## Slide 1
ZYCUS
Project Portfolio Health Report
Portfolio at Critical Red: Significant Delays and Execution Shortfalls Jeopardize Key S2P Implementations.
July 2026
Portfolio Status: Red

## Slide 2
Portfolio Snapshot
July 2026
The Zycus S2P portfolio is in a critical Red state, with both Titan and UniSan implementations facing severe challenges. Titan is significantly behind schedule with core 'Build' (51 days overdue) and 'Migration' (27 days overdue), hindering overall progress. UniSan, despite being technically ahead of schedule by 2 days, lags substantially with only 38.8% task completion against an expected 61.7% and has 42 critical 'Red' tasks outstanding.
RED
Zycus - Titan S2P Implementation
Critical Red state primarily due to 51-day delay on 'Build' and 27-day delay on 'Migration' milestones, compounded by...
>> Immediate re-baselining of the project plan, direct PM intervention to resolve critical...
RED
Zycus - UniSan S2P Implementation
Red status due to a substantial 22.9% deficit in task completion against plan, despite being reported as slightly ahead...
>> Deep dive into 175 'Not Started' and 42 'Red' tasks to identify root causes and blockers,...

## Slide 3
Trend Analysis
1
Both S2P implementation projects are currently rated Red, signaling widespread project health concerns across the portfolio.
2
Significant completion rate deficits and critical milestone delays are a recurring theme; Titan faces 51-day delays on 'Build', while UniSan shows a substantial 22.9% shortfall in task completion.
3
Issues with project plan integrity, dependency management, and Project Management engagement are evident, leading to critical path delays and potential decision-making bottlenecks.

## Slide 4
Emerging Risks
HIGH
Widespread Schedule & Completion Slippage
Both projects face critical delays on key milestones or significant deficits in task completion, threatening overall timelines and Go Live commitments.
HIGH
Project Management & Leadership Bottlenecks
Direct requests for PM engagement and a high number of unaddressed 'Red' tasks suggest potential leadership and facilitation gaps impacting progress.
HIGH
Underlying Project Plan & Tracking Flaws
Inconsistent milestone reporting (Titan) and a significant gap between 'ahead of schedule' and actual completion (UniSan) indicate foundational planning and tracking issues.
HIGH
Unresolved Critical Dependencies
Outstanding JDE mapping and data provisioning continue to block progress on key project phases for Titan, creating downstream impact.

## Slide 5
Executive Recommendations
1
Mandate immediate and comprehensive project plan reviews for both Titan and UniSan, focusing on logical dependencies, realistic scheduling, and re-baselining where necessary to ensure plan integrity.
2
Require the respective Project Managers to submit detailed recovery plans for all 'Red' and significantly delayed tasks/milestones within 48 hours, with clear ownership and committed dates.
3
Address the identified Project Management engagement and leadership gaps, particularly for Titan, ensuring critical path issues are resolved without delay and accountability is clear.
4
Establish a weekly portfolio review cadence with dedicated focus on resolving cross-project blockers and ensuring consistent reporting of project health metrics.

## Slide 6
Next Steps
▸ Schedule a direct meeting with the Project Managers for Titan and UniSan within 24 hours to review critical path issues and commitment to recovery plans.
▸ Request an urgent deep-dive session with the Titan project team to clarify milestone inconsistencies (e.g., Go Live vs. Migration/Hypercare status) and re-align the schedule.
▸ Engage the Delivery Lead to investigate the root causes of UniSan's completion rate deficit and ensure adequate resource allocation to address 'Red' tasks.
Portfolio Status
Red
CONFIDENTIAL – For executive use only